## Project schedule
[7 empty] | Project start: | [7 empty] | 2025-05-27
| EduDoc | [5 empty] | Display week: | [7 empty] | 1
[7 empty] | 2025-05-26 | [6 empty] | 2025-06-02 | [6 empty] | 2025-06-09 | [6 empty] | 2025-06-16 | [6 empty] | 2025-06-23 | [6 empty] | 2025-06-30 | [6 empty] | 2025-07-07 | [6 empty] | 2025-07-14
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2025-05-26 to 2025-07-20
 | time axis 2025-05-26 to 2025-07-20
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Initial Planning and Conceptualization
| Define goals | All Team | 100% | 2025-05-27 | 2025-05-28 | 2
| Wireframes / UI Sketches | Ojas Gharde | 100% | 2025-05-28 | 2025-06-01 | 5
| ERD and RACI Chart | kanishka garud | 100% | 2025-05-28 | 2025-06-01 | 5
| Gantt Chart | Yash Kannawar | 100% | 2025-05-28 | 2025-06-01 | 5
| Project Charter and Architecture | Vidya Bingi | 100% | 2025-05-28 | 2025-06-01 | 5
Design and Prototyping
| Create detailed wireframes | Ojas Gharde |  | 2025-06-02 | 2025-06-04 | 3
| Finalize database ERD | Kanishka garud |  | 2025-06-02 | 2025-06-04 | 3
| Finalize UI/UX designs | Yash Kannawar |  | 2025-06-02 | 2025-06-04 | 3
| Create API endpoint plan | Vidya Bingi |  | 2025-06-02 | 2025-06-05 | 4
| Sprint planning for development | All Team |  | 2025-06-03 | 2025-06-05 | 3
Development and Implementation
| Backend API development | Ojas Gharde |  | 2025-06-06 | 2025-06-12 | 7
| Frontend development | Kanishka garud |  | 2025-06-06 | 2025-06-12 | 7
| Document upload & retrieval feature | Yash Kannawar |  | 2025-06-08 | 2025-06-14 | 7
| Integration & testing | Vidya Bingi |  | 2025-06-13 | 2025-06-16 | 4
Testing, Deployment and Review
| Testing & bug fixing | Ojas Gharde |  | 2025-06-17 | 2025-06-18 | 2
| Deployment preparation | Kanishka Guard |  | 2025-06-19 | 2025-06-19 | 1
| Final deployment | Yash Kannawar |  | 2025-06-19 | 2025-06-20 | 2
| Project documentation & demo | Vidya Bingi |  | 2025-06-19 | 2025-06-20 | 2